## Roadmap (hidden)
| Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15
Core Experience
| Skinned Redemption | Expand 1-T-M | TE Rewrite | New P-A-F Page | Incentivized Sharing 2
| Incentivized Sharing | Delay SMS/E-mail | New Redemption | Redemption Email
Authentication
| Native Backend | Release UI | No Auth | No Auth
Delayed Auth
Social/Sharing
| Back-End Sharing | SMS Opt-In |  | Additional Networks
FB/Twitter Following
Merchant
| Release Dashboard |  | E-mail/SMS Reports | Modal/Treat This | Turn Key | Turn Key | Turn Key
Customer Visuals
Marketing Pixel
Admin/Internal |  |  | Clone Give_Flows
Infrastructure
|  | Automated Tests |  | API Rewrite | API Rewrite | API Rewrite | API Rewrite | API Rewrite
|  |  |  | Automated Tests |  | Automated Tests |  | Automated Tests
|  | GIVE 0 | GIVE 1 | GIVE 2
|  | AUTH 0 | MERCHANT 0 | AUTH 1
AUTH 1

## Roadmap-Phasing
Here was a rough roadmap we used at Treater, the main point was the show the progression for each feature (X axis) and phasing (Y axis). At the bottom in the sprints
we arranged how these would be worked on together
|  | Authentication (AUTH) | Give/View/Redeem (GIVE) | Social/Sharing (SHARE) | Incentives Engine (INCENT) | Merchant (MERCHANT) | Admin Tools (ADMIN) | Infrastructure (INFRA)
| Next Up (0) | Integrate LinkedIN | New redeem page for rewards | Individual link on confirmation | Incentivize Redeems | Customer table/export | Realign product vs gf fields
|  | Auth from P-A-F page |  |  |  | New Visualizations
| Next + 1 | Link Social Networks | TE: Send offer to receivers | FB Permission on Messaging Page | TE: Send more to get reward | Turn Key Phase I | New give_flow creator
|  |  | White Labeling Phase I |  | TE: Your friend redeemed |  | Preview Give Flows
|  |  | Post-xaction messaging changes |  | Incentivize Receiver to Give
|  |  | TE: Add email/SMS post-xaction |  | Enable rewards across xactions
| Next + 2 | Additional Social Networks | White Labeling Phase II |  | Rewards progress UI | Customer Segmentation | Internal Dashboard
|  | E-mail/SMS redemption verification | New Off-Network UI/UX |  | Incentivize Views | Split Campaign Analytics
TE: Redemption info
| Next + 3 | Native Auth | Embedded Treater Experience |  | Recipient Chooses Reward | Turn Key Phase II
|  |  | Send directly from P-A-F page |  |  | Self-Provisioning/Billing
|  | Sprint 10 | SPRINT 11 | SPRINT 12
|  | AUTH 0 | GIVE 1 | GIVE 2
|  | GIVE 0 | SHARE 1 | GIVE 3
|  | SHARE 0 | INCENT 1 | ADMIN 1
|  | INCENT 0 | ADMIN 0
MERCH 0